## Tasks
ID | Subject | Trucker | Estimated Duration | Description | Dependencies
1 | Requirement gathering & analysis | Business Analyst | 8 | Collect functional and non‑functional requirements for the task‑splitting API, including security, performance and integration points with the existing system. | System.Int32[]
2 | API specification (OpenAPI) | Business Analyst | 6 | Define endpoint contract, request/response schemas, authentication, error codes and rate‑limits for the new API. | System.Int32[]
3 | Solution design & architecture | Solution Architect | 6 | Design high‑level architecture, data model changes, interaction diagram with existing services and choose technology stack (e.g., FastAPI + PostgreSQL). | System.Int32[]
4 | Integration diagram update | Solution Architect | 2 | Create updated system integration diagram showing the new API flow and data exchange. | System.Int32[]
5 | Repository branch & CI pipeline extension | DevOps Engineer | 4 | Create a feature branch, add CI jobs for linting, unit testing and static analysis for the new module. | System.Int32[]
6 | Task‑splitting endpoint implementation | Backend Developer | 12 | Implement the POST /tasks/split endpoint, handle authentication, request validation and orchestrate the split service. | System.Int32[]
7 | Split algorithm development | Backend Developer | 10 | Write the core logic that divides a parent task into child tasks based on configurable rules (by size, priority, deadline, etc.). | System.Int32[]
8 | Validation & error handling | Backend Developer | 4 | Add comprehensive input validation, business‑rule checks and standardized error responses (400/409/500). | System.Int32[]
9 | Unit test suite | QA Engineer | 8 | Write unit tests for endpoint controller, split algorithm and validation layers covering happy and error paths. | System.Int32[]
10 | Integration tests | QA Engineer | 6 | End‑to‑end tests that invoke the API against a test instance of the existing system, verifying data persistence and downstream effects. | System.Int32[]
11 | API documentation update | Technical Writer | 4 | Add the new endpoint to the OpenAPI spec, generate Swagger UI pages and write usage examples. | System.Int32[]
12 | CI/CD pipeline enhancements | DevOps Engineer | 4 | Add deployment steps for the new service, integrate automated API contract validation and publish artifacts. | System.Int32[]
13 | Staging deployment & smoke testing | DevOps Engineer | 4 | Deploy the updated application to a staging environment and run smoke tests to verify endpoint availability. | System.Int32[]
14 | Production rollout | DevOps Engineer | 2 | Promote the new version to production with zero‑downtime strategy and monitor initial traffic. | System.Int32[]
15 | Monitoring & alerting setup | DevOps Engineer | 3 | Add Prometheus metrics and Grafana dashboards for the new endpoint, configure alerts for latency and error rate. | System.Int32[]